## ReadMe
2023-06-07 | cre: | Andy
2023-06-07 | upd: | Andy
References
| Seq | Topic | Folder | Document
| 1 | scope is on EDW specific artifacts
| 2 | DOMO migration is managed / calculated indipendently | DOMO to PBI | To PBI - Strategy and Data.xlsx
| 3 | basically no business or analysis documents are available (BA, DA, Minutes, …) | Confluence_Data
| 4 | basically no SQL scripts are available | Projects by BU
| 5 | Enhancment Projects (EDW 2.0) - ideas but no infra, methods, … in place |  | see tab 'work sheet' top10 ff
| 6 | Enhancements hard / no reliable / to estimate |  | see tab 'work sheet' top10 ff
7
8
9
10
11

## Work Sheet
[8 empty] | Totals | 103.23 |  | 6 | 97.23 | 97.23 | hours | 8 | h/day
[8 empty] | finished | 3.4 | F | 0 | 3.4 | 12.1538 | days | 50% | available h/day
| filer = 0 for Top Levels | [6 empty] | Missing | 0 | M | 0 | 0 | 24.3075 | days | 5 | days/week
[8 empty] | Ongoing | 0.6 | O | 0 | 0.6 | 4.8615 | weeks remaining work
[8 empty] | Planned | 99.23 | P | 6 | 93.23
Top1 | Top2 | Top3 | Top4 | Topic | Abstract | Description | No of Objects | Effort / Object | Totals hours | Status | Effort / Spent | Remaining Spent | Links / References Folder and Documents
1 | 0 | 0 | 0 | Repository of all objects
1 | 0 | 1 | 0 | EDW Objects | central Master document | overall 683 objects (tables, views) | 683 | 0.01 | 6.83 | P | 6 | 0.83 | Project Domains | EDW_TABLES.xlsx
1 | 0 | 2 | 0 | SQL Scripts | spread on SharePoint or offline |  | 10 | 0.05 | 0.5 | O |  | 0.5 | EDW Templates | Semantic View Documentation
1 | 0 | 3 | 0 | Documents | spread on SharePoint or offline |  | 2 | 0.05 | 0.1 | O |  | 0.1 | Projects by BU
2 | 0 | 0 | 0 | EDW Objects | [7 empty] | 0
2 | 1 | 0 | 0 | from DEV |  | no match with TEST / PROD | [5 empty] | 0
2 | 1 | 1 | 0 | Schema: LND_TB |  | lot of orphaned, dead objects … | [5 empty] | 0
2 | 1 | 1 | 1 | assign Business Purpose |  |  | 78 | 0.1 | 7.8 | P |  | 7.8
2 | 1 | 1 | 2 | assign Naming Conventions, Classification |  |  | 78 | 0.1 | 7.8 | P |  | 7.8
2 | 1 | 2 | 0 | Schema: INT_TB | [7 empty] | 0
2 | 1 | 2 | 1 | assign Business Purpose |  |  | 154 | 0.1 | 15.4 | P |  | 15.4
2 | 1 | 2 | 2 | assign Naming Conventions, Classification |  |  | 154 | 0.1 | 15.4 | P |  | 15.4
2 | 1 | 3 | 0 | Schema: SEM_MRT_VW | [7 empty] | 0
2 | 1 | 3 | 1 | assign Business Purpose |  |  | 110 | 0.1 | 11 | P |  | 11
2 | 1 | 3 | 2 | assign Naming Conventions, Classification |  |  | 110 | 0.1 | 11 | P |  | 11
2 | 1 | 4 | 0 | Schema: others | [7 empty] | 0
2 | 1 | 4 | 1 | assign Business Purpose |  |  |  | 1 | 0 | P |  | 0
2 | 1 | 4 | 2 | assign Naming Conventions, Classification |  |  |  | 1 | 0 | P |  | 0
2 | 2 | 0 | 0 | from TEST | best: ignore TEST and built from scratch | no match with DEV / PROD | [5 empty] | 0
2 | 2 | 1 | 0 | Schema: LND_TB | [7 empty] | 0
2 | 2 | 1 | 1 | assign Business Purpose | different to Dec AND PROD - WHY ? |  | 21 | 0 | 0 | P |  | 0
2 | 2 | 1 | 2 | assign Naming Conventions, Classification | different to Dec AND PROD - WHY ? |  | 21 | 0 | 0 | P |  | 0
2 | 2 | 2 | 0 | Schema: INT_TB | [7 empty] | 0
2 | 2 | 2 | 1 | assign Business Purpose | different to Dec AND PROD - WHY ? |  | 71 | 0 | 0 | P |  | 0
2 | 2 | 2 | 2 | assign Naming Conventions, Classification | different to Dec AND PROD - WHY ? |  | 71 | 0 | 0 | P |  | 0
2 | 2 | 3 | 0 | Schema: SEM_MRT_VW | [7 empty] | 0
2 | 2 | 3 | 1 | assign Business Purpose | different to Dec AND PROD - WHY ? |  | 43 | 0 | 0 | P |  | 0
2 | 2 | 3 | 2 | assign Naming Conventions, Classification | different to Dec AND PROD - WHY ? |  | 43 | 0 | 0 | P |  | 0
2 | 2 | 4 | 0 | Schema: others | EDW_BKP_TB | owner is ? | [5 empty] | 0
2 | 2 | 4 | 1 | assign Business Purpose |  |  | 4 | 0.1 | 0.4 | P |  | 0.4
2 | 2 | 4 | 2 | assign Naming Conventions, Classification |  |  | 4 | 0.1 | 0.4 | P |  | 0.4
2 | 3 | 0 | 0 | from PROD |  | no match with TEST / DEV | [5 empty] | 0
2 | 3 | 1 | 0 | Schema: LND_TB | [7 empty] | 0
2 | 3 | 1 | 1 | assign Business Purpose |  |  | 20 | 0.1 | 2 | P |  | 2
2 | 3 | 1 | 2 | assign Naming Conventions, Classification |  |  | 20 | 0.1 | 2 | P |  | 2
2 | 3 | 2 | 0 | Schema: INT_TB | [7 empty] | 0
2 | 3 | 2 | 1 | assign Business Purpose |  |  | 54 | 0.1 | 5.4 | P |  | 5.4
2 | 3 | 2 | 2 | assign Naming Conventions, Classification |  |  | 54 | 0.1 | 5.4 | P |  | 5.4
2 | 3 | 3 | 0 | Schema: SEM_MRT_VW | [7 empty] | 0
2 | 3 | 3 | 1 | assign Business Purpose |  |  | 34 | 0.1 | 3.4 | P |  | 3.4
2 | 3 | 3 | 2 | assign Naming Conventions, Classification |  | can include missing parts, to be reviwed | 34 | 0.1 | 3.4 | F |  | 3.4
2 | 3 | 4 | 0 | Schema: others | EDW_BKP_TB, EDW_SNDBX_TB | owner is ? | [5 empty] | 0
2 | 3 | 4 | 1 | assign Business Purpose |  |  | 25 | 0.1 | 2.5 | P |  | 2.5
2 | 3 | 4 | 2 | assign Naming Conventions, Classification |  |  | 25 | 0.1 | 2.5 | P |  | 2.5
3 | 0 | 0 | 0 | assign Naming Conventions, Classification | [7 empty] | 0
3 | 1 | 0 | 0 | SQL Scripts | [7 empty] | 0
3 | 1 | 1 | 0 | from DEV |  |  |  | 1 |  | P |  | 0
3 | 1 | 2 | 0 | from TEST |  |  |  | 0.5 |  | P |  | 0
3 | 1 | 3 | 0 | from PROD |  |  |  | 0.5 |  | F |  | 0
3 | 2 | 0 | 0 | Documents | [7 empty] | 0
3 | 2 | 1 | 0 | Business Projects |  |  |  | 0.5 |  | P |  | 0
3 | 2 | 2 | 0 | Management |  |  |  | 0.5 |  | P |  | 0
3 | 2 | 3 | 0 | Issues / Tickets |  |  |  | 0.5 |  | P |  | 0
10 | 0 | 0 | 0 | Enhancing EDW Models | [7 empty] | 0
10 | 0 | 1 | 0 | case.1 = business requirement | [7 empty] | 0
10 | 0 | 1 | 1 | find or re-create business docs |  |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 2 | model logical model(s) | maybe reverse enginnering is needed |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 3 | implement on DEV | KANBAN, anything ? |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 4 | Internal Test and Sign-Off |  |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 5 | implement on TEST |  |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 6 | UAT |  |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 7 | Business Sign-Off |  |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 8 | implement on PROD |  |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 9 | Internal (DevOps) Sign-Off |  |  |  |  | 0 | P |  | 0
10 | 0 | 1 | 10 | Close / Feeze Product Release |  |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 0 | case.2 = planned re-design | aka EDW 2.0 | [6 empty] | 0
10 | 0 | 2 | 2 | model logical model(s) | maybe reverse enginnering is needed |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 3 | implement on DEV | KANBAN, anything ? |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 4 | Internal Test and Sign-Off |  |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 5 | implement on TEST |  |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 6 | UAT |  |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 7 | Business Sign-Off |  |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 8 | implement on PROD |  |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 9 | Internal (DevOps) Sign-Off |  |  |  |  | 0 | P |  | 0
10 | 0 | 2 | 10 | Close / Feeze Product Release |  |  |  |  | 0 | P |  | 0
10 | 1 | 0 | 0 | Define Infrastructure / Operation Model | [7 empty] | 0
10 | 1 | 1 | 0 | Roles and Responsibilities | who is doing what |  |  |  | 0 | P |  | 0
10 | 1 | 2 | 0 | Document Locations | SharePoint Structures |  |  |  | 0 | P |  | 0
10 | 1 | 3 | 0 | Document Types / Artifacts |  |  |  |  | 0 | P |  | 0
10 | 1 | 4 | 0 | PM Methods ? KANBAN, anything ? |  |  |  |  | 0 | P |  | 0
10 | 1 | 5 | 0 | Modeling Approach | Tool / Team / Paper |  |  |  | 0 | P |  | 0
10 | 1 | 6 | 0 | Release Management Approach |  |  |  |  | 0 | P |  | 0
10 | 1 | 7 | 0 | Deployment Approach DEV-TEST |  |  |  |  | 0 | P |  | 0
10 | 1 | 8 | 0 | Testing, Sign-Off Approach |  |  |  |  | 0 | P |  | 0
10 | 1 | 9 | 0 | Deployment Approach TEST-PROD |  |  |  |  | 0 | P |  | 0
10 | 1 | 10 | 0 | Cleanup DEV-TEST |  |  |  |  | 0 | P |  | 0
10 | 1 | 11 | 0 | Close / Freeze / Release Approach |  |  |  |  | 0 | P |  | 0